## Sheet1
Lessons Learned Database - Updated 17JUN2013
# | Title | Action
1 | Ownership has been defined as a key issue. Assign the task to them and hold them to it. | Strong TCDs in place. Provide a list of priorities early on
2 | Time Management needs to be improved. | Ensure we start 5 min in advance and facilitator to prep the speaker in advance regarding the time and to make sure they give eye contact to the facilitator near the end
3 | In-person first call for volunteers is required | At least 1 1/2 month in advance. Chapters to provide a list of volunteers at all times.
4 | Printing should be resolved earlier | Last minute printing is not feasible. Freeze the aganda as early as possible. Minimum of 1 week prior to event.
5 | Roll out the charter to people to let them know what we stand for. | Action to President.
6 | Try to do a dry run prior to the event. | Ask volunteers to come early to ensure we have a dry run or meet the volunteers one day prior.
7 | Survey form needs to be handy | Print the survey form and follow it up with a web survey
8 | Marketing has been weaker to students and other companies. | Make a list of companies and universities that we market to and ensure we have a SPOC.
9 | Change NAYGN focus from utility chapter to area chapter | speak with the core team to ensure we have a good understanding of that. Action to President
10 | Ensure that NAYGN is not limited to Engineering | Spread the word across all facets of the company. Do a NAYGN Presentation of what we do and a news release.
11 | Use Google hangouts/skype meetings | Ensure evening meetings are okay with the volunteers and core to make this happen.
12 | Connect with universities for funding the event room | Action to Chapter Leads
13 | Core Meetings need to be held frequently. | Action to President.
14 | Compile a list of potential locations where events can be held. | Action to President.
15 | Provide generic access to communications group for each chapter to upload events | Action to US-NAYGN
16 | Utilize Google Drive for Document Sharing.
17 | provide a list of duties for volunteers and upload this to the NAYGN website.
18
19
20
21
22
23
24
25
26
27
28
29